## Sheet1
Gantt Chart showing task timeline
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Formative Tasks
Host virtual focus group | bar: Year 1 Q1
Contact Information Gathering | bar: Year 1 Q3
Contact Domestic Base | bar: Year 1 Q3
Contact Global Bases | bar: Year 1 Q4 to Year 2 Q1
Base Site Logistics Planning | bar: Year 2 Q3 to Year 2 Q4
Implementation Tasks
Retrospective Survey | bar: Year 1 Q2
Domestic Base Survey | bar: Year 2 Q1
Global Base Survey | bar: Year 2 Q2 to Year 3 Q2
Data Cleaning | bar: Year 1 Q3; Year 2 Q3 to Year 3 Q3
Base Site Visit | bar: Year 3 Q1
Data Analysis | bar: Year 1 Q3 to Year 1 Q4; Year 2 Q3 to Year 3 Q4
Dissemination Tasks
Conference Presentations (3) | bar: Year 1 Q4; Year 2 Q3; Year 3 Q3
Manuscript Submission (2) | bar: Year 2 Q1; Year 3 Q4
Online Blog Article (2) | bar: Year 2 Q4
Workshop/Public Forum | bar: Year 2 Q3; Year 3 Q2
Evaluative Tasks
Bi-Weekly Meetings
Annual Assessment