## Sheet1
Table 2. Timeline and anticipated collaborative distribution of effort |  | Contribution (%)
| Activity | LG | MA | SU | GA1
Year 1 | Host virtual focus group to discuss survey, implications, and framing | 34 | 33 | 33 | 0
Q1: | Deploy a retrospective, online survey targeting the national population of veterans | 30 | 30 | 40 | 0
9/19- 12/19 | Data Analysis of Pilot and Retrospective Survey | 25 | 25 | 50 | 0
Q2: | Refinment of Survey Materials | 25 | 25 | 50 | 0
12/19- 3/19 | Draft/Finalize coding protocol | 30 | 20 | 50 | 0
| Compile list of contact information for targeted global bases for year 2 | 10 | 40 | 0 | 50
Q3: | Recruit participants from a domestic base - comparison group for global surveys | 30 | 60 | 0 | 10
3/19- 6/19 | Analyze data and write up results for manuscript #1 | 30 | 30 | 30 | 10
| Submit conference proposal #1 | 33 | 33 | 33 | 1
Q4: | Recruit and hire Graduate Assistant | 40 | 20 | 40 | 0
6/19- 8/19 | Finalize and Submit first manuscript (Criminology focus) | 40 | 20 | 40 | 0
| NSF Reporting | 60 | 20 | 20 | 0
Year 2 | Train Graduate Assistant | 50 | 10 | 20 | 20
Q1: | Contact approximately 35 bases to survey globally | 30 | 60 | 0 | 10
9/20- 12/20 | Develop Active Duty Interview Protocol | 40 | 40 | 10 | 10
| Develop Stakeholder Interview Protocol | 40 | 40 | 10 | 10
| Determine and Plan all Logistics for Site Visit | 30 | 30 | 20 | 0
Q2: | Submit conference proposal #2 | 33 | 33 | 33 | 1
12/20- 3/20 | Deploy survey to at least one domestic base | 10 | 10 | 50 | 30
| Deploy survey to subset of global bases | 20 | 20 | 40 | 20
Year 2 | Draft and submit article a high impact blog (e.g. Monkey Cage) | 20 | 50 | 20 | 10
Q3: | Host workshop on experimental survey design at Boise State University | 5 | 5 | 75 | 20
3/20- 6/20 | Analyze data, write up results, and submit manuscript #2 (literacy) | 20 | 20 | 40 | 20
Q4: | Analyze data, write up results, and submit manuscript #3 (quality indicators) | 20 | 20 | 40 | 20
6/20- 8/20 | Submit conference proposal #2 (literacy and quality indicators) | 20 | 20 | 40 | 20
| NSF Reporting | 60 | 10 | 10 | 20
Year 3 | Site visit of one high profile military base and surrounding area relevant to the study | 35 | 35 | 30 | 0
Q1: | Interviews of Active Duty | 35 | 35 | 30 | 10
9/21- 12/21 | Interview Stakeholders | 35 | 35 | 30 | 30
Q2: | Interview Local Stakeholders | 35 | 35 | 30 | 20
12/21- 3/21 | Data Gather regarding site details | 5 | 35 | 35 | 25
| Continue survey for any bases that delay granting permission | 5 | 5 | 60 | 30
| Final cleaning of survey data | 0 | 0 | 70 | 30
Year 3 | Code Qualitative data | 60 | 10 | 10 | 20
Q3: | Analyze data, write up results, and submit manuscript #2 (Criminology) | 10 | 40 | 20 | 20
3/21- 6/21 | Analyze data, write up results, and submit manuscript #3 ( International Relations) | 40 | 10 | 20 | 20
| Finalize and distribute quantitative brief | 10 | 10 | 60 | 20
| Target one public oriented blog site (e.g. The Conversation) for public discussion of final results | 20 | 40 | 20 | 20
Q4: | Host public forum on research at Boise State University | 40 | 15 | 15 | 30
6/21- 8/21 | Complete NSF final project report | 60 | 10 | 10 | 20

## Sheet2
User Interface
60% | 60%
20% | 20%
20% | 20%
Requirements Gathering | 45%
45% | 35%
35% | 30%
30% | 60%
User Interface | 20%
60% | 20%
20% | 30%
20% | 35%
Query Formulation | 35%
30% | 10%
35% | 40%
35% | 50%
Spelling | 60%
10% | 20%
40% | 20%
50% | 25%
User Interface | 50%
60% | 25%
20% | 30%
20% | 50%
Query Formulation | 20%
25% | 10%
50% | 40%
25% | 50%
Quality of Results | 20%
30% | 20%
50% | 60%
20% | 60%
Spelling | 20%
10% | 20%
40% | 60%
50% | 20%
Ontologies | 20%
20% | 25%
20% | 50%
60% | 25%
User Interface | 30%
60% | 50%
20% | 20%
20% | 20%
User Evaluation | 40%
60% | 30%
20% | 10%
20% | 40%
Query Formulation | 50%
25% | 20%
50% | 20%
25% | 60%
Quality of Results | 20%
30% | 20%
50% | 60%
20% | 33%
Over/under specifying Queries | 33%
20% | 34%
40%
30%
Spelling
10%
40%
50%
Ontologies
20%
20%
60%
Result Snippets
20%
20%
60%
AVERAGE CONTRIBUTIONS
33%
33%
34%